## Sheet1
Module | Tasks | Status | Completion date | Sub tasks
Project Type Classification | Milestones and milestone-related columns must be stored in the database based on project type | Completed | 2026-04-07 | Saving milestone defination and milestone column in db for AHLOA
Constraints | Constraints should be maintained at the project level Inite the seed data for the AHLOA constarints Update the logic for gantt, calenadr, week wise summary based on the constarints | Completed | 2026-04-10 | Admin functionality
Filters | Fetch all filters based on AHLOA gate checks | Completed | 2026-04-07
Dashboard summary | Fetch the site wise / status wise count -> On track , In progress, critical , blocked | Completed
Week-wise Summary | Provide week-wise overall site status counts | Completed | 2026-04-08
Calendar | Enable site-wise milestone drilldown with current status for a given start and end date | Completed | 2026-04-08
Analytics | Pending milestone count → Site countPending milestone name → Site countDrilldown to site-wise details for pending counts or pending milestone sites | Not started yet | 2026-04-09
Prerequisite | Project-wise skip and unskip functionality | Not started yet | 2026-04-09 | Admin functionality
User | User-wise filter save, update | Not started yet | 2026-04-10
| Retrieval -> User-based milestone completion days tracking | Not started yet | 2026-04-10
Gantt charts | For 13 milestones different. (Construction gantt) | Completed | 2026-04-07
| For 3 milestone different (Scope phase gantt) | Completed | 2026-04-07
Vendor capacity | Based on available data | Blocked | On hold
Pace constarints | Based on logic for AHLOA | Blocked | On hold
AI assistant | Filter change , Simulation intent | Blocked | On hold
Excel upload | No clarity | Blocked | On hold
RFI tab | No clarity | Blocked | On hold
Overall Calculation Logic | Forecasted construction start date calculated using milestone planned date, actual completion date, and SLA (left to right flow) Keep existing logic unchanged; introduce additional reverse (right to left) calculation for delay tracking | In Progress | 3
Calculation Direction | Left to right (prerequisite to next milestone) Add right to left logic starting from planned construction start date to calculate delay days | Not started yet
Anchor Field | No fixed anchor; derived from milestone flow Use pj_p_4225_construction_start_finish as anchor date for reverse calculation | Not started yet
Site Filtering | All sites considered Include only sites where planned construction start date is NOT NULL; exclude NULL records | Not started yet
SLA Handling | SLA applied per milestone in forward calculation Apply SLA in reverse direction; support all SLA types (user-based SLA / History / Default) | Not started yet | 1
Delay Calculation | No explicit delay tracking per milestone Calculate delay days per milestone based on reverse SLA logic; update delayed forecast date in Gantt chart and all relevant tabs | Not started yet | 0.5
Major Blocker Identification | Not available Identify and display major blocker (prerequisite causing delay) with note “Delayed due to” | Not started yet | 0.2
Extra Buffer Rule | “+4 days after all prerequisites complete” applied Remove this rule completely | Not started yet
Excel Upload Purpose | Used to update/swap forecasted construction start date only Extend to allow updating actual completion date for any milestone and site | Not started yet | 2
All Tabs | Tabs shown based on left-to-right Gantt logic calculating forecasted date for all sites based on milestone and SLA Tabs should be shown in two views: 1. Based on forecasted CX start date (real-time SLA-based) 2. Based on right-to-left logic using existing forecasted CX start date | Not started yet | 1

## Sheet2
Based on new requirements
Sr no | Requirement Title | Description | Status
1 | Prerequisite Skip/Unskip | Provide functionality for users to skip/unskip prerequisites market-wise (user-based control) instead of admin-based control as in NTM. | Dev done
2 | Forecast Date Handling | If the forecasted date falls in the past, use CX start reference from pl_p_4225_construction_start_finish only in those cases. | Dev done
3 | GC Null Handling | If GC (General Contractor) is null, display a note such as: "GC not yet assigned." | Dev done
4 | Gantt Chart Enhancements | Add seconds-level granularity in the Gantt chart (Survey Gantt). Include separate tabs for Survey and Construction, each having: Calendar, Week-wise Summary, and Analytics. | In progress
5 | On-Hold Vendor Capacity Data | Retrieve ON HOLD vendor capacity data from Arvind. | In progress
6 | Pace Constraint Handling | Handle pace constraints same as NTM. Change: After adjusting the CX start date, recalculate milestone-wise status for all sites across all tabs. | Dev done
7 | AI Assistant Scope | AI Assistant should: • Allow skip/unskip of prerequisites (market-wise, user-based) • Allow changing filters • Respond to greeting queries • Answer simulation-related queries | In progress
8 | Excel Data Handling | Excel format remains same as NTM. Replace (swap) the CX start date with uploaded data, without recalculating CX start again. | Dev done
Past Tasks
| User based SLA | User based milestone wise sla management | Dev done
| Project Type Classification | Milestones and milestone-related columns must be stored in the database based on project type | Dev done
| Constraints | Constraints should be maintained at the project level Inite the seed data for the AHLOA constarints Update the logic for gantt, calenadr, week wise summary based on the constarints | Dev done
| Filters | Fetch all filters based on AHLOA gate checks | Dev done
| Dashboard summary | Fetch the site wise / status wise count -> On track , In progress, critical , blocked | Dev done
| Week-wise Summary | Provide week-wise overall site status counts | Dev done
| Calendar | Enable site-wise milestone drilldown with current status for a given start and end date | Dev done
| Analytics | Pending milestone count → Site countPending milestone name → Site countDrilldown to site-wise details for pending counts or pending milestone sites | Dev done