## Sheet1
SITE_ID | REGION | MARKET | PROJECT_ID | Notes/Remarks
TMO_CA_19862 | Central | San Francisco | PJ-2026-824586 | Construction crew confirmed mobilization for September 15th 2026. All prereqs cleared. CX target holding firm.
TMO_CA_54942 | South | Los Angeles | PJ-2026-313487 | Permit appeal filed by neighbor 03/12. City council review scheduled mid-April. Earliest realistic CX is 10/05/2026 assuming favorable ruling. Currently blocked pending permitting outcome.
TMO_CA_82512 | Central | San Francisco | PJ-2026-112038 | Steel delivery slipped 3 weeks (vendor cited mill backlog). Crew now redeployed to a different site. Targeting Wk-43 once steel lands. Site is blocked at the moment.
TMO_CO_38080 | Central | Denver | PJ-2026-665427 | Tracking to original plan. Expected start week 40. No issues reported by GC.
TMO_CO_91678 | Central | Denver | PJ-2026-429164 | Forecast 2026-08-25. Walk-down complete, BOM in AIMS, NTP issued.
TMO_CO_46193 | Central | Denver | PJ-2026-559044 | Wildfire smoke advisory in effect; OSHA halt on outdoor work. CX pushed to first week of November (~11/02/2026). Currently blocked by air-quality conditions.
TMO_TX_71208 | South | Dallas | PJ-2026-418992 | Targeting 9/22/26. Risk: GC capacity tight in Dallas through August — may slip a week if vendor doesn't confirm crew by Friday.
TMO_TX_22041 | South | Houston | PJ-2026-882103 | Customer requested antenna swap mid-design. Re-engineering required. Hold on construction. Revised CX no earlier than 11/15/2026. Site is blocked pending updated drawings.
TMO_TX_88914 | South | Houston | PJ-2026-723801 | Was previously blocked on power distribution; utility company expedited drop on 04/18. Back on track for Wk-38 CX (~Sept 14).
TMO_AZ_11203 | South | Phoenix | PJ-2026-100912 | In progress.
TMO_AZ_67742 | South | Phoenix | PJ-2026-441018 | Project paused by customer pending Q3 capex review. No new CX date until after the budget meeting on 6/15. Effectively blocked.