## Q0_Filters_PR2,_PR3,_PR4_(Hard_
QUERY 0: Base Filter Validation — How Many Sites Pass the 3 Core Filters?
Pre-Requisite: | Filters #2, #3, #4 (Hard Cost Vendor, Plan Type, POR Year)
Purpose: | Before checking any pre-requisite, validate how many sites survive the base WHERE clause. If this returns 0 rows, all downstream queries will also be empty.
Client Requirement (Exact from Doc): | Client Req #2: Hard Cost Vendor Assignment → Contains "NOKIA" Client Req #3: Plan Type → Other than "Equipment Upgrade" & "FOA" Client Req #4: POR Planned Year → Contains "2026 Build Plan" Implicit: pj_project_status = Active, pj_p_4225_construction_start_finish IS NOT NULL
DB Columns Used: | pj_hard_cost_vendor_assignment_po — VARCHAR — vendor company name por_plan_type — VARCHAR — POR plan classification por_regional_dev_initiatives — VARCHAR — regional initiative label pj_project_status — VARCHAR — project lifecycle status pj_p_4225_construction_start_finish — VARCHAR — planned construction start (4225 P Date)
Expected Output: | Total row count + breakdown by region/market. If 0, check filter values individually.
Assumptions & Open Items: | 1. Table name: pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined 2. ILIKE used for case-insensitive matching (PostgreSQL syntax) 3. pj_hard_cost_vendor_assignment_po may contain full company name like "nokia solutions and networks us llc" 4. por_plan_type values are exact strings (case-sensitive NOT IN) 5. por_regional_dev_initiatives may have multiple values; ILIKE %2026 Build Plan% handles substring match
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 0: BASE FILTER VALIDATION -- Purpose : Verify how many sites pass the 3 core client filters -- Expected: Non-zero count. If 0 → filters are too restrictive or data issue -- ═══════════════════════════════════════════════════════════════════════ SELECT COUNT(*) AS total_sites_passing_filters, COUNT(DISTINCT s_site_id) AS unique_sites, COUNT(DISTINCT rgn_region) AS regions_covered, COUNT(DISTINCT m_market) AS markets_covered, -- Breakdown to see what's in the filtered data rgn_region AS region, m_market AS market, COUNT(*) AS sites_per_market FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL GROUP BY rgn_region, m_market ORDER BY rgn_region, m_market; -- ═══════════════════════════════════════════════════════════════════════ -- DIAGNOSTIC: If above returns 0, run these to check each filter alone -- ═══════════════════════════════════════════════════════════════════════ -- Check Filter #2 alone: How many rows have NOKIA vendor? -- SELECT COUNT(*), pj_hard_cost_vendor_assignment_po -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- GROUP BY pj_hard_cost_vendor_assignment_po LIMIT 20; -- Check Filter #3 alone: What plan types exist? -- SELECT por_plan_type, COUNT(*) -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- GROUP BY por_plan_type ORDER BY COUNT(*) DESC; -- Check Filter #4 alone: What regional dev initiatives exist? -- SELECT por_regional_dev_initiatives, COUNT(*) -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE por_regional_dev_initiatives IS NOT NULL -- GROUP BY por_regional_dev_initiatives ORDER BY COUNT(*) DESC LIMIT 20;

## Q1_PR1_Entitlement_Complete
QUERY 1: Pre-Requisite #1 — Entitlement Complete
Pre-Requisite: | #1 Entitlement Complete
Purpose: | Check if RAN Entitlement is complete. Uses COALESCE logic: if actual date exists → complete; else fall back to planned date. This is the FIRST gate in the construction readiness chain.
Client Requirement (Exact from Doc): | Client Doc Row 1: Pre-requisite: Entitlement Complete Field Type: Date Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: pj_a_3710_ran_entitlement_complete_finish, pj_p_3710_ran_entitlement_complete_finish Filter: Check if "pj_a_3710_ran_entitlement_complete_finish" is non blank, then consider it as complete else take "pj_p_3710_ran_entitlement_complete_finish" date to pick planned date.
DB Columns Used: | pj_a_3710_ran_entitlement_complete_finish — VARCHAR — Actual finish date for MS 3710 pj_p_3710_ran_entitlement_complete_finish — VARCHAR — Planned finish date for MS 3710
Expected Output: | Per-site entitlement status: Complete (Actual) / Planned / Not Started, with dates.
Assumptions & Open Items: | 1. "Non blank" means IS NOT NULL AND value is not empty string 2. Actual date takes priority over planned date (COALESCE order) 3. If actual is populated → entitlement is DONE 4. If only planned exists → entitlement is SCHEDULED but not yet done 5. Both columns are VARCHAR; dates stored as text like "2025-12-09 10:21:06" 6. No date-diff calculation needed for this pre-requisite (no "X weeks before" rule)
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 1: PRE-REQUISITE #1 — ENTITLEMENT COMPLETE -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- If "pj_a_3710_ran_entitlement_complete_finish" is non-blank → complete -- Else take "pj_p_3710_ran_entitlement_complete_finish" as planned date -- -- Logic: COALESCE(actual, planned) — actual takes priority -- Stake Holder: T-Mobile -- Milestone: MS 3710 — RAN Entitlement Complete -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw column values (for manual inspection) pj_a_3710_ran_entitlement_complete_finish AS entitlement_actual_raw, pj_p_3710_ran_entitlement_complete_finish AS entitlement_planned_raw, -- Derived: Pick actual if available, else planned COALESCE( NULLIF(TRIM(pj_a_3710_ran_entitlement_complete_finish), ''), NULLIF(TRIM(pj_p_3710_ran_entitlement_complete_finish), '') ) AS entitlement_effective_date, -- Status determination CASE WHEN NULLIF(TRIM(pj_a_3710_ran_entitlement_complete_finish), '') IS NOT NULL THEN 'COMPLETE (Actual Date Exists)' WHEN NULLIF(TRIM(pj_p_3710_ran_entitlement_complete_finish), '') IS NOT NULL THEN 'PLANNED (Only Planned Date — Not Yet Complete)' ELSE 'NOT STARTED (Both Actual & Planned Are Blank)' END AS entitlement_status, -- Pass/Fail for Gantt readiness CASE WHEN NULLIF(TRIM(pj_a_3710_ran_entitlement_complete_finish), '') IS NOT NULL THEN 'PASS' WHEN NULLIF(TRIM(pj_p_3710_ran_entitlement_complete_finish), '') IS NOT NULL THEN 'PARTIAL (Planned Only)' ELSE 'FAIL' END AS prereq_1_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY entitlement_status DESC, -- Show failures first pj_p_4225_construction_start_finish ASC;

## Q2_PR2_Hard_Cost_Vendor_Assignm
QUERY 2: Pre-Requisite #2 — Hard Cost Vendor Assignment (Filter Validation)
Pre-Requisite: | #2 Hard Cost Vendor Assignment
Purpose: | This pre-requisite is already applied as a WHERE filter (ILIKE NOKIA). This query validates what vendor values exist and confirms the filter is working correctly.
Client Requirement (Exact from Doc): | Client Doc Row 2: Pre-requisite: Hard Cost Vendor Assignment Field Type: Text Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: (not specified — mapped to pj_hard_cost_vendor_assignment_po) Filter: Contains "NOKIA"
DB Columns Used: | pj_hard_cost_vendor_assignment_po — VARCHAR — vendor company name for hard cost PO Example values: "nokia solutions and networks us llc", "NOKIA"
Expected Output: | Distinct vendor values containing NOKIA + count of sites per vendor string.
Assumptions & Open Items: | 1. Client doc has no column name specified; we mapped to pj_hard_cost_vendor_assignment_po 2. ILIKE used for case-insensitive matching (handles "nokia", "NOKIA", "Nokia Solutions...") 3. This is a FILTER pre-requisite — it restricts the dataset, not a milestone date 4. All rows in the filtered dataset already pass this check by definition 5. If vendor name has variations (e.g., "nokia solutions and networks us llc"), all are included
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 2: PRE-REQUISITE #2 — HARD COST VENDOR ASSIGNMENT -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: Contains "NOKIA" -- This is a FILTER condition (already in WHERE clause) -- This query validates the filter is working + shows vendor distribution -- -- Stake Holder: T-Mobile -- Column Mapped: pj_hard_cost_vendor_assignment_po -- NOTE: Client doc did NOT specify a column name — this is our mapping assumption -- ═══════════════════════════════════════════════════════════════════════ -- Part A: Show distinct vendor values in the filtered dataset SELECT pj_hard_cost_vendor_assignment_po AS vendor_assignment_value, COUNT(*) AS site_count, COUNT(DISTINCT s_site_id) AS unique_sites FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL GROUP BY pj_hard_cost_vendor_assignment_po ORDER BY site_count DESC; -- Part B: Show what we're EXCLUDING (non-NOKIA vendors in the full dataset) -- Uncomment to run: -- SELECT -- pj_hard_cost_vendor_assignment_po AS vendor_value, -- COUNT(*) AS excluded_count -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE pj_hard_cost_vendor_assignment_po NOT ILIKE '%NOKIA%' -- OR pj_hard_cost_vendor_assignment_po IS NULL -- GROUP BY pj_hard_cost_vendor_assignment_po -- ORDER BY excluded_count DESC LIMIT 20;

## Q3_PR3_Plan_Type
QUERY 3: Pre-Requisite #3 — Plan Type (Filter Validation)
Pre-Requisite: | #3 Plan Type
Purpose: | This pre-requisite is already applied as a WHERE filter (NOT IN Equipment Upgrade, FOA). This query validates plan type distribution in the filtered dataset.
Client Requirement (Exact from Doc): | Client Doc Row 3: Pre-requisite: Plan Type Field Type: Text Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: POR:Plan Type → mapped to por_plan_type Filter: Other than "Equipment Upgrade" & "FOA"
DB Columns Used: | por_plan_type — VARCHAR — POR plan type classification (e.g., replacement, colo consolidation, magenta pace)
Expected Output: | Distinct plan types remaining after exclusion + site counts.
Assumptions & Open Items: | 1. Client says column is "POR:Plan Type" — mapped to por_plan_type in DB 2. NOT IN uses exact string match (case-sensitive) 3. If plan types have different casing (e.g., "equipment upgrade"), they won't be excluded 4. Verify: Does the DB have "Equipment Upgrade" exactly or a different case? 5. NULL plan types are NOT excluded by NOT IN — they pass through (NULL != any value is NULL, not TRUE)
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 3: PRE-REQUISITE #3 — PLAN TYPE -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: Other than "Equipment Upgrade" & "FOA" -- This is a FILTER condition (already in WHERE clause) -- -- Stake Holder: T-Mobile -- Client Column Reference: "POR:Plan Type" → mapped to por_plan_type -- -- IMPORTANT ASSUMPTION: NOT IN is CASE-SENSITIVE in PostgreSQL -- If DB has "equipment upgrade" (lowercase), it will NOT be excluded! -- Run Part B below to check actual values in the DB. -- ═══════════════════════════════════════════════════════════════════════ -- Part A: Plan types in the filtered dataset (what survived the filter) SELECT por_plan_type AS plan_type_value, COUNT(*) AS site_count, COUNT(DISTINCT s_site_id) AS unique_sites FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL GROUP BY por_plan_type ORDER BY site_count DESC; -- Part B: ALL plan types in full table (to check if case mismatch exists) -- Uncomment to run: -- SELECT por_plan_type, COUNT(*) -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE por_plan_type IS NOT NULL -- GROUP BY por_plan_type ORDER BY COUNT(*) DESC;

## Q4_PR4_POR_Planned_Year
QUERY 4: Pre-Requisite #4 — POR Planned Year (Filter Validation)
Pre-Requisite: | #4 POR Planned Year
Purpose: | This pre-requisite is already applied as a WHERE filter (ILIKE 2026 Build Plan). This query validates what regional dev initiative values exist.
Client Requirement (Exact from Doc): | Client Doc Row 4: Pre-requisite: POR Planned Year Field Type: Text Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: POR:Regional Dev Initiatives → mapped to por_regional_dev_initiatives Filter: Contains "2026 Build Plan"
DB Columns Used: | por_regional_dev_initiatives — VARCHAR — regional development initiative label (e.g., "2026 Build Plan")
Expected Output: | Distinct initiative values containing "2026 Build Plan" + site counts.
Assumptions & Open Items: | 1. Client says column is "POR:Regional Dev Initiatives" → mapped to por_regional_dev_initiatives 2. ILIKE with % wildcards handles substring match + case insensitivity 3. A single row could have value exactly "2026 Build Plan" or it could be part of a longer string 4. If the column has comma-separated values, ILIKE still catches it
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 4: PRE-REQUISITE #4 — POR PLANNED YEAR -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: Contains "2026 Build Plan" -- This is a FILTER condition (already in WHERE clause) -- -- Stake Holder: T-Mobile -- Client Column Reference: "POR:Regional Dev Initiatives" → por_regional_dev_initiatives -- ═══════════════════════════════════════════════════════════════════════ SELECT por_regional_dev_initiatives AS regional_dev_initiative_value, COUNT(*) AS site_count, COUNT(DISTINCT s_site_id) AS unique_sites FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL GROUP BY por_regional_dev_initiatives ORDER BY site_count DESC;

## Q5_PR5_CPO_Available
QUERY 5: Pre-Requisite #5 — CPO Available
Pre-Requisite: | #5 CPO Available
Purpose: | Check if Customer Purchase Order (CPO) number exists. This is a gate — construction cannot start without a CPO from T-Mobile.
Client Requirement (Exact from Doc): | Client Doc Row 5: Pre-requisite: CPO Available Field Type: Text Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: MS 1555 Construction Complete CPO # (custom field) Filter: Non Blanks
DB Columns Used: | cpo — VARCHAR — Customer Purchase Order number from T-Mobile (e.g., "2346454") ALTERNATIVE: ms1555_construction_complete_spo — if cpo is empty, try this column ALTERNATIVE: base_cpo_received — confirmation that base CPO was received
Expected Output: | Per-site CPO availability status: Available / Missing.
Assumptions & Open Items: | 1. Client says "MS 1555 Construction Complete CPO # (custom field)" 2. No EXACT column match in DB — we mapped to "cpo" as primary candidate 3. ALTERNATIVE columns to check if "cpo" is mostly NULL: - ms1555_construction_complete_spo - base_cpo_received - e2e_nsd_project_mgmt_cpo_number 4. "Non Blanks" means: IS NOT NULL AND != empty string 5. NULLIF(TRIM(col), '') handles both NULL and empty string cases 6. ⚠️ THIS IS A KEY ASSUMPTION — ask client to confirm which column is the CPO #
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 5: PRE-REQUISITE #5 — CPO AVAILABLE -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: "MS 1555 Construction Complete CPO # (custom field)" = Non Blanks -- ⚠️ ASSUMPTION: Mapped to "cpo" column — NO EXACT MATCH in DB metadata -- If most rows show "Missing", try alternative columns below -- -- Stake Holder: T-Mobile -- Gate Type: Must-have before construction -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Primary mapped column cpo AS cpo_number_raw, -- Alternative columns (uncomment to compare) -- ms1555_construction_complete_spo AS ms1555_spo_alt, -- base_cpo_received AS base_cpo_alt, -- e2e_nsd_project_mgmt_cpo_number AS e2e_cpo_alt, -- Status CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 'AVAILABLE (CPO # Exists)' ELSE 'MISSING (No CPO # Found)' END AS cpo_status, CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 'PASS' ELSE 'FAIL' END AS prereq_5_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_5_result ASC, -- FAILs first pj_p_4225_construction_start_finish ASC; -- ═══════════════════════════════════════════════════════════════════════ -- DIAGNOSTIC: Check all candidate CPO columns to find the right one -- Uncomment and run if cpo column shows mostly NULL -- ═══════════════════════════════════════════════════════════════════════ -- SELECT -- COUNT(*) AS total_rows, -- COUNT(NULLIF(TRIM(cpo), '')) AS cpo_populated, -- COUNT(NULLIF(TRIM(ms1555_construction_complete_spo), '')) AS ms1555_spo_populated, -- COUNT(NULLIF(TRIM(base_cpo_received), '')) AS base_cpo_populated, -- COUNT(NULLIF(TRIM(e2e_nsd_project_mgmt_cpo_number), '')) AS e2e_cpo_populated -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL;

## Q6_PR6_If_Site_Survey_Completed
QUERY 6: Pre-Requisite #6 — Site Survey Completed (Talon Drone)
Pre-Requisite: | #6 If Site Survey Completed
Purpose: | Check if Talon View drone site survey has been completed. This is required before scoping and NTP can proceed.
Client Requirement (Exact from Doc): | Client Doc Row 6: Pre-requisite: If site survey completed Field Type: Text Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: MS 1321 Talon View Drone SVCS CPO # (custom field) Filter: Non Blanks
DB Columns Used: | ms_1321_talon_view_drone_svcs_actual — TIMESTAMP — actual date of Talon drone survey ms_1321_talon_view_drone_svcs_cit — VARCHAR — CIT number for Talon drone SPO ms_1321_talon_view_drone_svcs_spo — VARCHAR — SPO number for Talon services
Expected Output: | Per-site survey status: Complete / Pending, with survey date.
Assumptions & Open Items: | 1. Client says "MS 1321 Talon View Drone SVCS CPO # (custom field)" 2. Mapped to ms_1321_talon_view_drone_svcs_actual as primary (actual completion date) 3. Also checking ms_1321_talon_view_drone_svcs_cit as backup (CIT = completion indicator) 4. "Non Blanks" = if either actual date OR CIT is populated → survey is done 5. Stake Holder is Nokia (Nokia manages the Talon drone surveys) 6. No date-diff calculation needed — just a non-blank check
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 6: PRE-REQUISITE #6 — SITE SURVEY COMPLETED (TALON DRONE) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: "MS 1321 Talon View Drone SVCS CPO # (custom field)" = Non Blanks -- Mapped to: ms_1321_talon_view_drone_svcs_actual (primary) -- ms_1321_talon_view_drone_svcs_cit (secondary) -- -- Stake Holder: Nokia -- Milestone: MS 1321 — Talon View Drone Services -- Gate Type: Must-complete before scoping/NTP -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw columns ms_1321_talon_view_drone_svcs_actual AS survey_actual_date_raw, ms_1321_talon_view_drone_svcs_cit AS survey_cit_raw, ms_1321_talon_view_drone_svcs_spo AS survey_spo_raw, -- Status CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL THEN 'COMPLETE (Actual Survey Date Exists)' WHEN NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 'COMPLETE (CIT Exists — Survey Done)' ELSE 'PENDING (No Survey Date or CIT Found)' END AS survey_status, CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL OR NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 'PASS' ELSE 'FAIL' END AS prereq_6_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_6_result ASC, pj_p_4225_construction_start_finish ASC;

## Q7_PR7_BOM_Ready
QUERY 7: Pre-Requisite #7 — BOM Ready (≥4 Weeks Before 4225 P Date)
Pre-Requisite: | #7 BOM Ready
Purpose: | Check if Bill of Materials (BOM) has been submitted in BAT system, AND if it was submitted at least 4 weeks (28 days) before the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 7: Pre-requisite: BOM Ready Field Type: Date Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: pj_a_3850_bom_submitted_bom_in_bat_finish Filter: Non blanks & Date diff should be a Minimum of 4 weeks before 4225 P Date
DB Columns Used: | pj_a_3850_bom_submitted_bom_in_bat_finish — VARCHAR — Actual BOM submission date (MS 3850) pj_p_3850_bom_submitted_bom_in_bat_finish — VARCHAR — Planned BOM submission date pj_p_4225_construction_start_finish — VARCHAR — 4225 P Date (planned construction start)
Expected Output: | Per-site BOM status with date diff calculation: Met (≥4 wks) / At Risk (<4 wks) / Not Ready.
Assumptions & Open Items: | 1. "4225 P Date" = pj_p_4225_construction_start_finish (PLANNED construction start) 2. "4 weeks" = 28 calendar days 3. Date diff = 4225_P_Date - BOM_actual_date (positive if BOM was before construction) 4. Both columns are VARCHAR — need ::date or TO_DATE() casting 5. NULLIF(TRIM(col), '') handles empty strings before casting 6. If actual is NULL but planned exists, BOM is NOT ready (only actual counts) 7. "Non blanks" applies to the ACTUAL date column, not planned
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 7: PRE-REQUISITE #7 — BOM READY (≥4 WEEKS BEFORE 4225 P DATE) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: pj_a_3850_bom_submitted_bom_in_bat_finish -- Filter: Non blanks & Date diff should be Minimum of 4 weeks before 4225 P Date -- -- Key Calculation: -- days_before_4225 = pj_p_4225_construction_start_finish - pj_a_3850_bom_submitted_bom_in_bat_finish -- Must be >= 28 days -- -- Stake Holder: T-Mobile -- Milestone: MS 3850 — BOM Submitted (BOM in BAT) -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, -- Anchor date pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw BOM columns pj_a_3850_bom_submitted_bom_in_bat_finish AS bom_actual_raw, pj_p_3850_bom_submitted_bom_in_bat_finish AS bom_planned_raw, -- Date diff calculation (only if actual is non-blank) CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL THEN (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) ELSE NULL END AS days_bom_before_4225, -- Status with thresholds CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NULL THEN 'NOT READY (Actual BOM Date is Blank)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 'MET (BOM Ready ≥4 Weeks Before Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 0 THEN 'AT RISK (BOM Ready But <4 Weeks Before Cx Start)' ELSE 'LATE (BOM Submitted AFTER Cx Start Date)' END AS bom_ready_status, CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 'PASS' WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL THEN 'PARTIAL (Date exists but <28 days gap)' ELSE 'FAIL' END AS prereq_7_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_7_result ASC, days_bom_before_4225 ASC NULLS FIRST;

## Q8_PR8_BOM_Material_avl_in_MSL
QUERY 8: Pre-Requisite #8 — BOM Material avl in MSL (≥1 Week Before 4225 P Date)
Pre-Requisite: | #8 BOM Material avl in MSL
Purpose: | Check if BOM material has been received at MSL (warehouse) AND if it happened at least 1 week (7 days) before the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 8: Pre-requisite: BOM Material avl in MSL Field Type: Date Stake Holder: T-Mobile Table: ndpd_mbt_tmobile_macro_combined Column: pj_a_3875_bom_received_bom_in_aims_finish Filter: Non blanks & Date diff should be a Minimum of 1 week before 4225 P Date
DB Columns Used: | pj_a_3875_bom_received_bom_in_aims_finish — Actual finish date for MS 3875 pj_p_3875_bom_received_bom_in_aims_finish — Planned finish date for MS 3875 pj_p_4225_construction_start_finish — 4225 P Date (anchor)
Expected Output: | Per-site status with date diff: Met (≥1 wk) / At Risk / Not Ready.
Assumptions & Open Items: | 1. "4225 P Date" = pj_p_4225_construction_start_finish 2. "1 week" = 7 calendar days 3. Date diff = 4225_P_Date - actual_date (positive = before construction start) 4. Column is VARCHAR — needs ::date casting 5. NULLIF(TRIM(col), '') protects against empty strings 6. Only ACTUAL date counts — planned date shown for reference only
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 8: PRE-REQUISITE #8 — BOM MATERIAL AVL IN MSL (≥1 WEEK BEFORE 4225 P DATE) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: pj_a_3875_bom_received_bom_in_aims_finish -- Filter: Non blanks & Date diff = Minimum 1 week before 4225 P Date -- -- Calculation: 4225_P_Date - actual_date >= 7 days -- Stake Holder: T-Mobile -- Milestone: MS 3875 -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw columns pj_a_3875_bom_received_bom_in_aims_finish AS actual_date_raw, pj_p_3875_bom_received_bom_in_aims_finish AS planned_date_raw, -- Date diff (only if actual exists) CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL THEN (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) ELSE NULL END AS days_before_4225, -- Status CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NULL THEN 'NOT READY (Actual Date is Blank)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 'MET (≥1 Week Before Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 0 THEN 'AT RISK (<1 Week But Before Cx Start)' ELSE 'LATE (After Cx Start Date)' END AS status, CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 'PASS' WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL THEN 'PARTIAL' ELSE 'FAIL' END AS prereq_8_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_8_result ASC, days_before_4225 ASC NULLS FIRST;

## Q9_PR9_Material_Pickup_by_GC
QUERY 9: Pre-Requisite #9 — Material Pickup by GC (≥1 Week Before 4225 P Date)
Pre-Requisite: | #9 Material Pickup by GC
Purpose: | Check if GC has picked up materials from MSL AND if it happened at least 1 week (7 days) before the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 9: Pre-requisite: Material Pickup by GC Field Type: Date Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: pj_a_3925_msl_pickup_date_finish Filter: Non blanks & Date diff should be a Minimum of 1 week before 4225 P Date
DB Columns Used: | pj_a_3925_msi_pickup_date_finish — Actual finish date for MS 3925 pj_p_3925_msl_pickup_date_finish — Planned finish date for MS 3925 pj_p_4225_construction_start_finish — 4225 P Date (anchor)
Expected Output: | Per-site status with date diff: Met (≥1 wk) / At Risk / Not Ready.
Assumptions & Open Items: | 1. "4225 P Date" = pj_p_4225_construction_start_finish 2. "1 week" = 7 calendar days 3. Date diff = 4225_P_Date - actual_date (positive = before construction start) 4. Column is VARCHAR — needs ::date casting 5. NULLIF(TRIM(col), '') protects against empty strings 6. Only ACTUAL date counts — planned date shown for reference only
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 9: PRE-REQUISITE #9 — MATERIAL PICKUP BY GC (≥1 WEEK BEFORE 4225 P DATE) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: pj_a_3925_msl_pickup_date_finish -- Filter: Non blanks & Date diff = Minimum 1 week before 4225 P Date -- -- Calculation: 4225_P_Date - actual_date >= 7 days -- Stake Holder: Nokia -- Milestone: MS 3925 -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw columns pj_a_3925_msi_pickup_date_finish AS actual_date_raw, pj_p_3925_msl_pickup_date_finish AS planned_date_raw, -- Date diff (only if actual exists) CASE WHEN NULLIF(TRIM(pj_a_3925_msi_pickup_date_finish), '') IS NOT NULL THEN (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) ELSE NULL END AS days_before_4225, -- Status CASE WHEN NULLIF(TRIM(pj_a_3925_msi_pickup_date_finish), '') IS NULL THEN 'NOT READY (Actual Date is Blank)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 'MET (≥1 Week Before Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 0 THEN 'AT RISK (<1 Week But Before Cx Start)' ELSE 'LATE (After Cx Start Date)' END AS status, CASE WHEN NULLIF(TRIM(pj_a_3925_msi_pickup_date_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 'PASS' WHEN NULLIF(TRIM(pj_a_3925_msi_pickup_date_finish), '') IS NOT NULL THEN 'PARTIAL' ELSE 'FAIL' END AS prereq_9_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_9_result ASC, days_before_4225 ASC NULLS FIRST;

## Q10_PR10_NTP_Received
QUERY 10: Pre-Requisite #10 — NTP Received (≥4 Weeks Before 4225 P Date)
Pre-Requisite: | #10 NTP Received
Purpose: | Check if Notice to Proceed (NTP) has been accepted by GC AND if it happened at least 4 weeks (28 days) before the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 10: Pre-requisite: NTP Received Field Type: Date Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: pj_a_4100_construction_ntp_accepted_by_gc_finish Filter: Non blanks & Date diff should be a Minimum of 4 weeks before 4225 P Date
DB Columns Used: | pj_a_4100_construction_ntp_accepted_by_gc_finish — Actual finish date for MS 4100 pj_p_4100_construction_ntp_accepted_by_gc_finish — Planned finish date for MS 4100 pj_p_4225_construction_start_finish — 4225 P Date (anchor)
Expected Output: | Per-site status with date diff: Met (≥4 wks) / At Risk / Not Ready.
Assumptions & Open Items: | 1. "4225 P Date" = pj_p_4225_construction_start_finish 2. "4 weeks" = 28 calendar days 3. Date diff = 4225_P_Date - actual_date (positive = before construction start) 4. Column is VARCHAR — needs ::date casting 5. NULLIF(TRIM(col), '') protects against empty strings 6. Only ACTUAL date counts — planned date shown for reference only
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 10: PRE-REQUISITE #10 — NTP RECEIVED (≥4 WEEKS BEFORE 4225 P DATE) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: pj_a_4100_construction_ntp_accepted_by_gc_finish -- Filter: Non blanks & Date diff = Minimum 4 weeks before 4225 P Date -- -- Calculation: 4225_P_Date - actual_date >= 28 days -- Stake Holder: Nokia -- Milestone: MS 4100 -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Raw columns pj_a_4100_construction_ntp_accepted_by_gc_finish AS actual_date_raw, pj_p_4100_construction_ntp_accepted_by_gc_finish AS planned_date_raw, -- Date diff (only if actual exists) CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL THEN (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) ELSE NULL END AS days_before_4225, -- Status CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NULL THEN 'NOT READY (Actual Date is Blank)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 'MET (≥4 Weeks Before Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 0 THEN 'AT RISK (<4 Weeks But Before Cx Start)' ELSE 'LATE (After Cx Start Date)' END AS status, CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 'PASS' WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL THEN 'PARTIAL' ELSE 'FAIL' END AS prereq_10_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_10_result ASC, days_before_4225 ASC NULLS FIRST;

## Q11_PR11_SPO
QUERY 11: Pre-Requisite #11 — SPO (≥6 Weeks From TODAY to 4225 P Date)
Pre-Requisite: | #11 SPO
Purpose: | Check if Total Supplier Purchase Order value/number is non-blank AND there are at least 6 weeks (42 days) from TODAY to the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 11: Pre-requisite: SPO Field Type: Text Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: (Column not specified by client) Filter: Non blanks. 4225 P Date - TODAY & Date diff should be Minimum of 6 weeks
DB Columns Used: | total_spo — VARCHAR — Total Supplier Purchase Order value/number pj_p_4225_construction_start_finish — 4225 P Date (anchor) CURRENT_DATE — today's date (dynamic — changes each run)
Expected Output: | Per-site status: Met / At Risk / Missing, with days-to-4225 from today.
Assumptions & Open Items: | 1. "4225 P Date - TODAY" means: pj_p_4225_construction_start_finish::date - CURRENT_DATE 2. "6 weeks" = 42 calendar days 3. This checks TIME REMAINING until construction, not when the prerequisite was done 4. "Non blanks" = the column must have a value (IS NOT NULL AND != empty) 5. Both conditions must be true: column non-blank AND enough time remains 6. Stake Holder: Nokia 7. ⚠️ Client did NOT specify a column name for SPO 8. We mapped to "total_spo" — ALTERNATIVES to check: - confirm_receipt_of_base_pos_and_spos_generated - base_spo_requested_date - confirm_split_spo 9. Ask client to confirm which column represents "SPO"
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 11: PRE-REQUISITE #11 — SPO (≥6 WEEKS FROM TODAY) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: (Column not specified by client) -- Filter: Non blanks. 4225 P Date - TODAY ≥ 6 weeks (42 days) -- -- TWO conditions must BOTH be true: -- 1) total_spo IS NOT NULL and not empty -- 2) pj_p_4225_construction_start_finish::date - CURRENT_DATE >= 42 -- -- Stake Holder: Nokia -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Days remaining from today to planned construction start (pj_p_4225_construction_start_finish::date - CURRENT_DATE) AS days_to_4225_from_today, -- Raw column value total_spo AS spo_raw, -- Alternative SPO columns (uncomment to compare) -- confirm_receipt_of_base_pos_and_spos_generated AS alt_spo_confirm, -- base_spo_requested_date AS alt_spo_date, -- confirm_split_spo AS alt_split_spo, -- Status CASE WHEN NULLIF(TRIM(total_spo), '') IS NULL THEN 'MISSING (SPO Value is Blank)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 'MET (Value Exists & ≥6 Weeks to Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 0 THEN 'AT RISK (Value Exists But <6 Weeks to Cx Start)' ELSE 'OVERDUE (Cx Start Date Has Passed)' END AS status, CASE WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 'PASS' WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL THEN 'PARTIAL (Value exists but time insufficient)' ELSE 'FAIL' END AS prereq_11_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_11_result ASC, days_to_4225_from_today ASC;

## Q12_PR12_Crane
QUERY 12: Pre-Requisite #12 — Crane (≥2 Weeks From TODAY to 4225 P Date)
Pre-Requisite: | #12 Crane
Purpose: | Check if Indicates whether crane is required (yes/no from scoping) is non-blank AND there are at least 2 weeks (14 days) from TODAY to the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 12: Pre-requisite: Crane Field Type: Text Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: scoping_package_crane_required Filter: Non blanks. 4225 P Date - TODAY & Date diff should be Minimum of 2 weeks
DB Columns Used: | scoping_package_crane_required — VARCHAR — Indicates whether crane is required (yes/no from scoping) pj_p_4225_construction_start_finish — 4225 P Date (anchor) CURRENT_DATE — today's date (dynamic — changes each run)
Expected Output: | Per-site status: Met / At Risk / Missing, with days-to-4225 from today.
Assumptions & Open Items: | 1. "4225 P Date - TODAY" means: pj_p_4225_construction_start_finish::date - CURRENT_DATE 2. "2 weeks" = 14 calendar days 3. This checks TIME REMAINING until construction, not when the prerequisite was done 4. "Non blanks" = the column must have a value (IS NOT NULL AND != empty) 5. Both conditions must be true: column non-blank AND enough time remains 6. Stake Holder: Nokia 7. Values typically: "yes", "no" — both are valid (means decision was made) 8. "Non blanks" = the crane decision HAS been made, regardless of yes/no 9. NULL or empty = crane requirement not yet determined
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 12: PRE-REQUISITE #12 — CRANE (≥2 WEEKS FROM TODAY) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: scoping_package_crane_required -- Filter: Non blanks. 4225 P Date - TODAY ≥ 2 weeks (14 days) -- -- TWO conditions must BOTH be true: -- 1) scoping_package_crane_required IS NOT NULL and not empty -- 2) pj_p_4225_construction_start_finish::date - CURRENT_DATE >= 14 -- -- Stake Holder: Nokia -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Days remaining from today to planned construction start (pj_p_4225_construction_start_finish::date - CURRENT_DATE) AS days_to_4225_from_today, -- Raw column value scoping_package_crane_required AS crane_raw, -- Status CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NULL THEN 'MISSING (Crane Value is Blank)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'MET (Value Exists & ≥2 Weeks to Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 0 THEN 'AT RISK (Value Exists But <2 Weeks to Cx Start)' ELSE 'OVERDUE (Cx Start Date Has Passed)' END AS status, CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL THEN 'PARTIAL (Value exists but time insufficient)' ELSE 'FAIL' END AS prereq_12_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_12_result ASC, days_to_4225_from_today ASC;

## Q13_PR13_Access
QUERY 13: Pre-Requisite #13 — Access (≥2 Weeks From TODAY to 4225 P Date)
Pre-Requisite: | #13 Access
Purpose: | Check if NDPc quality session title — indicates scoping session was created is non-blank AND there are at least 2 weeks (14 days) from TODAY to the planned construction start date.
Client Requirement (Exact from Doc): | Client Doc Row 13: Pre-requisite: Access Field Type: Text Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: NDPC Scoping Session Title/Name Filter: Non blanks. 4225 P Date - TODAY & Date diff should be Minimum of 2 weeks
DB Columns Used: | scop_title — VARCHAR — NDPc quality session title — indicates scoping session was created pj_p_4225_construction_start_finish — 4225 P Date (anchor) CURRENT_DATE — today's date (dynamic — changes each run)
Expected Output: | Per-site status: Met / At Risk / Missing, with days-to-4225 from today.
Assumptions & Open Items: | 1. "4225 P Date - TODAY" means: pj_p_4225_construction_start_finish::date - CURRENT_DATE 2. "2 weeks" = 14 calendar days 3. This checks TIME REMAINING until construction, not when the prerequisite was done 4. "Non blanks" = the column must have a value (IS NOT NULL AND != empty) 5. Both conditions must be true: column non-blank AND enough time remains 6. Stake Holder: Nokia 7. Client says "NDPC Scoping Session Title/Name" 8. Mapped to scop_title — NDPc session title (e.g., "RC010363A_central_detroit_coverage_strategy") 9. Non-blank means a scoping session exists → access has been evaluated
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 13: PRE-REQUISITE #13 — ACCESS (≥2 WEEKS FROM TODAY) -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: NDPC Scoping Session Title/Name -- Filter: Non blanks. 4225 P Date - TODAY ≥ 2 weeks (14 days) -- -- TWO conditions must BOTH be true: -- 1) scop_title IS NOT NULL and not empty -- 2) pj_p_4225_construction_start_finish::date - CURRENT_DATE >= 14 -- -- Stake Holder: Nokia -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Days remaining from today to planned construction start (pj_p_4225_construction_start_finish::date - CURRENT_DATE) AS days_to_4225_from_today, -- Raw column value scop_title AS access_raw, scop_owner AS scoping_session_owner, scop_created_on_new AS scoping_session_created, -- Status CASE WHEN NULLIF(TRIM(scop_title), '') IS NULL THEN 'MISSING (Access Value is Blank)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'MET (Value Exists & ≥2 Weeks to Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 0 THEN 'AT RISK (Value Exists But <2 Weeks to Cx Start)' ELSE 'OVERDUE (Cx Start Date Has Passed)' END AS status, CASE WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL THEN 'PARTIAL (Value exists but time insufficient)' ELSE 'FAIL' END AS prereq_13_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_13_result ASC, days_to_4225_from_today ASC;

## Q14_PR14_Site_Ready_for_Ca
QUERY 14: Pre-Requisite #14 — Site Ready for Ca / NDPC COP Session (≥2 Weeks From TODAY)
Pre-Requisite: | #14 Site Ready for Ca
Purpose: | Check if NDPC COP (Close-Out Package) session exists or checklist is accepted AND there are at least 2 weeks from TODAY to planned construction start.
Client Requirement (Exact from Doc): | Client Doc Row 14: Pre-requisite: Site ready for Ca Field Type: Text Stake Holder: Nokia Table: ndpd_mbt_tmobile_macro_combined Column: NDPC COP Session Title/Name Filter: Non blanks. 4225 P Date - TODAY & Date diff should be Minimum of 2 weeks
DB Columns Used: | scop_checklist_accepted_by_customer — VARCHAR — T-Mobile accepted the final checklist ms_1559_cop_approved_by_t_mobile_actual — TIMESTAMP — COP approved by T-Mobile date cop_approval_type — VARCHAR — Type of COP approval used pj_p_4225_construction_start_finish — 4225 P Date (anchor)
Expected Output: | Per-site COP/site-readiness status: Met / At Risk / Not Ready.
Assumptions & Open Items: | 1. Client says "NDPC COP Session Title/Name" — NO exact column match in DB 2. ⚠️ Mapped to scop_checklist_accepted_by_customer (checklist acceptance) 3. ALSO checking ms_1559_cop_approved_by_t_mobile_actual (COP approval date) 4. Either column being non-blank = site readiness confirmed 5. "2 weeks" = 14 calendar days from TODAY to 4225 P Date 6. COP typically happens LATE in project lifecycle — many rows may be NULL 7. ⚠️ Ask client to confirm: Is this about COP approval or a different "Ca" session?
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 14: PRE-REQUISITE #14 — SITE READY FOR CA / NDPC COP SESSION -- ═══════════════════════════════════════════════════════════════════════ -- Client Requirement: -- Column: NDPC COP Session Title/Name -- Filter: Non blanks. 4225 P Date - TODAY ≥ 2 weeks (14 days) -- -- ⚠️ NO EXACT COLUMN MATCH — Using proxy columns: -- 1) scop_checklist_accepted_by_customer -- 2) ms_1559_cop_approved_by_t_mobile_actual -- -- Stake Holder: Nokia -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, -- Days remaining (pj_p_4225_construction_start_finish::date - CURRENT_DATE) AS days_to_4225_from_today, -- Raw columns (check which has data) scop_checklist_accepted_by_customer AS checklist_accepted_raw, ms_1559_cop_approved_by_t_mobile_actual AS cop_approved_date_raw, cop_approval_type AS cop_type_raw, written_email_cop_approval AS cop_email_raw, -- Status CASE WHEN NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NULL AND ms_1559_cop_approved_by_t_mobile_actual IS NULL THEN 'NOT READY (No COP Acceptance or Approval Found)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'MET (COP Exists & ≥2 Weeks to Cx Start)' WHEN (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 0 THEN 'AT RISK (COP Exists But <2 Weeks to Cx Start)' ELSE 'OVERDUE (Cx Start Date Has Passed)' END AS site_ready_status, CASE WHEN (NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL) AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' WHEN NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL THEN 'PARTIAL (COP exists but time insufficient)' ELSE 'FAIL' END AS prereq_14_result FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY prereq_14_result ASC, days_to_4225_from_today ASC; -- ═══════════════════════════════════════════════════════════════════════ -- DIAGNOSTIC: Check which COP-related columns have data -- ═══════════════════════════════════════════════════════════════════════ -- SELECT -- COUNT(*) AS total, -- COUNT(NULLIF(TRIM(scop_checklist_accepted_by_customer), '')) AS checklist_accepted, -- COUNT(ms_1559_cop_approved_by_t_mobile_actual) AS cop_approved, -- COUNT(NULLIF(TRIM(cop_approval_type), '')) AS cop_type, -- COUNT(NULLIF(TRIM(written_email_cop_approval), '')) AS cop_email -- FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined -- WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL;

## Q15_SUMMARY
QUERY 15: SUMMARY — All Pre-Requisites Combined (Pass/Fail per Site)
Pre-Requisite: | ALL (1-14)
Purpose: | Single query showing PASS/FAIL for every pre-requisite per site in one row. Use this AFTER running individual queries to verify.
Client Requirement (Exact from Doc): | All 14 pre-requisites from client document combined into one summary view.
DB Columns Used: | All columns from Queries 1-14.
Expected Output: | One row per site with 14 PASS/FAIL columns + total_passed count + overall_readiness.
Assumptions & Open Items: | 1. ALL assumptions from individual queries apply 2. NULLIF(TRIM(col), '') is used consistently for VARCHAR null-safe checks 3. Filters #2, #3, #4 are in WHERE clause (not as PASS/FAIL columns) 4. overall_readiness = ALL PRE-REQS MET only if prereqs 1,5,6,7,8,9,10,11,12,13,14 all PASS 5. total_passed shows how many of 11 checks passed (max = 11)
SQL QUERY:
-- ═══════════════════════════════════════════════════════════════════════ -- QUERY 15: SUMMARY — ALL PRE-REQUISITES COMBINED -- ═══════════════════════════════════════════════════════════════════════ -- One row per site showing PASS/FAIL for every pre-requisite -- Filters #2, #3, #4 are already in WHERE clause -- -- Total checkable pre-reqs: 11 (Reqs 1, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14) -- Reqs 2, 3, 4 are filter conditions, not milestone checks -- ═══════════════════════════════════════════════════════════════════════ SELECT s_site_id AS site_id, pj_project_id AS project_id, pj_project_name AS project_name, m_market AS market, rgn_region AS region, pj_p_4225_construction_start_finish AS planned_cx_start_4225, (pj_p_4225_construction_start_finish::date - CURRENT_DATE) AS days_to_cx_start, -- ══ PRE-REQ #1: Entitlement ══ CASE WHEN NULLIF(TRIM(COALESCE(pj_a_3710_ran_entitlement_complete_finish, pj_p_3710_ran_entitlement_complete_finish)), '') IS NOT NULL THEN 'PASS' ELSE 'FAIL' END AS prereq_01_entitlement, -- ══ PRE-REQ #5: CPO ══ CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 'PASS' ELSE 'FAIL' END AS prereq_05_cpo, -- ══ PRE-REQ #6: Site Survey ══ CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL OR NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 'PASS' ELSE 'FAIL' END AS prereq_06_survey, -- ══ PRE-REQ #7: BOM Ready ≥4wk ══ CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 'PASS' ELSE 'FAIL' END AS prereq_07_bom_ready, -- ══ PRE-REQ #8: BOM Material ≥1wk ══ CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 'PASS' ELSE 'FAIL' END AS prereq_08_bom_material, -- ══ PRE-REQ #9: Material Pickup ≥1wk ══ CASE WHEN pj_a_3925_msi_pickup_date_finish IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 'PASS' ELSE 'FAIL' END AS prereq_09_material_pickup, -- ══ PRE-REQ #10: NTP ≥4wk ══ CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 'PASS' ELSE 'FAIL' END AS prereq_10_ntp, -- ══ PRE-REQ #11: SPO ≥6wk from today ══ CASE WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 'PASS' ELSE 'FAIL' END AS prereq_11_spo, -- ══ PRE-REQ #12: Crane ≥2wk from today ══ CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' ELSE 'FAIL' END AS prereq_12_crane, -- ══ PRE-REQ #13: Access ≥2wk from today ══ CASE WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' ELSE 'FAIL' END AS prereq_13_access, -- ══ PRE-REQ #14: Site Ready ≥2wk from today ══ CASE WHEN (NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL) AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 'PASS' ELSE 'FAIL' END AS prereq_14_site_ready, -- ══ TOTAL PASSED COUNT ══ ( CASE WHEN NULLIF(TRIM(COALESCE(pj_a_3710_ran_entitlement_complete_finish, pj_p_3710_ran_entitlement_complete_finish)), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL OR NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN pj_a_3925_msi_pickup_date_finish IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN (NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL) AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END ) AS total_passed_out_of_11, -- ══ OVERALL READINESS ══ CASE WHEN ( CASE WHEN NULLIF(TRIM(COALESCE(pj_a_3710_ran_entitlement_complete_finish, pj_p_3710_ran_entitlement_complete_finish)), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL OR NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN pj_a_3925_msi_pickup_date_finish IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN (NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL) AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END ) = 11 THEN 'ALL PRE-REQS MET (11/11)' ELSE 'GAPS EXIST (' ¦¦ (11 - ( CASE WHEN NULLIF(TRIM(COALESCE(pj_a_3710_ran_entitlement_complete_finish, pj_p_3710_ran_entitlement_complete_finish)), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(cpo), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN ms_1321_talon_view_drone_svcs_actual IS NOT NULL OR NULLIF(TRIM(ms_1321_talon_view_drone_svcs_cit), '') IS NOT NULL THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3850_bom_submitted_bom_in_bat_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3850_bom_submitted_bom_in_bat_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_3875_bom_received_bom_in_aims_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3875_bom_received_bom_in_aims_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN pj_a_3925_msi_pickup_date_finish IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_3925_msi_pickup_date_finish::date) >= 7 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(pj_a_4100_construction_ntp_accepted_by_gc_finish), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - pj_a_4100_construction_ntp_accepted_by_gc_finish::date) >= 28 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(total_spo), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 42 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scoping_package_crane_required), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN NULLIF(TRIM(scop_title), '') IS NOT NULL AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END + CASE WHEN (NULLIF(TRIM(scop_checklist_accepted_by_customer), '') IS NOT NULL OR ms_1559_cop_approved_by_t_mobile_actual IS NOT NULL) AND (pj_p_4225_construction_start_finish::date - CURRENT_DATE) >= 14 THEN 1 ELSE 0 END ))::text ¦¦ ' pre-reqs failing)' END AS overall_readiness FROM pwc_macro_staging_schema.stg_ndpd_mbt_tmobile_macro_combined WHERE -- ═══════════════════════════════════════════════════════════════ -- BASE FILTERS (Applied to ALL queries as per Client Requirements) -- ═══════════════════════════════════════════════════════════════ -- CLIENT REQ #2: Hard Cost Vendor Assignment -- Assumption: Column "pj_hard_cost_vendor_assignment_po" contains vendor company name -- Condition : Must contain "NOKIA" (case-insensitive match using ILIKE) -- Purpose : Restricts dataset to only Nokia-assigned sites pj_hard_cost_vendor_assignment_po ILIKE '%NOKIA%' -- CLIENT REQ #3: Plan Type -- Assumption: Column "por_plan_type" holds the POR plan classification -- Condition : Exclude "Equipment Upgrade" and "FOA" plan types -- Purpose : Focus on new build / site modification projects only AND por_plan_type NOT IN ('Equipment Upgrade', 'FOA') -- CLIENT REQ #4: POR Planned Year -- Assumption: Column "por_regional_dev_initiatives" contains initiative labels -- Condition : Must contain "2026 Build Plan" substring (case-insensitive) -- Purpose : Scope to 2026 Build Plan year only AND por_regional_dev_initiatives ILIKE '%2026 Build Plan%' -- IMPLICIT FILTER: Active Projects Only -- Assumption: Only active projects are relevant for construction readiness AND pj_project_status = 'Active' -- IMPLICIT FILTER: Must have a planned construction start date -- Assumption: "4225 P Date" = pj_p_4225_construction_start_finish -- This is the ANCHOR date for all "X weeks before" calculations AND pj_p_4225_construction_start_finish IS NOT NULL ORDER BY total_passed_out_of_11 DESC, pj_p_4225_construction_start_finish ASC;